## Recuro Pre-Discovery
Recuro : Discovery Engagement - Preparation and Readiness Planning
Task No. | Task Name | Start Date | End Date | Owner | Progress | Comments
1 | Pre-Discovery Activities |  |  | Ramesh / Anand
1.1 | Identify resources for key roles - Program Lead, Business Consultant, EA, Tech Lead and DevOps and Testing Specialist | 2025-03-02 | 02-14-2025 | Anand / Sundar / Rachika | IN PROGRESS. On Track to identify ALL key candidates by 2/14
1.1.1 | Program Manager (offer to be rolled out 2/7) | 2025-03-02 | 2025-07-02 | Anand | Identified (external). Offer to be rolled out. | Offer to be rolled out 2/7
1.1.2 | Business Consultant (3 profiles being interviewed - should identify candidate by 2/14 and possible start by 2/24) | 2025-03-02 | 02-14-2025 | Anand / Ramesh | Yet to identify. Have backup plans | Target to close the candidate identification by 2/14 and onboard by 2/24 Progress made: 2/7: Evaluated internal candidate Varun Khandewal on 2/7. However candidate does NOT have the expertise handling enterprise level consulting engagements within Healthcare. Keeping him in standby while other external profiles are reviewed. 2/6: Additional external profiles shared. Interviews scheduled for 2/7 and 2/10. Discussions to consider Sami as Domain consultant for the discovery is also considered. 2/5: Original identified candidate (Krithika Vijaychandran) is a drop. Confirmed on 2/5.
1.1.3 | Enterprise Architect (Simon Albett from UK v/s Debashish Dalui) | 2025-03-02 | 2025-12-02 | Karthik Hari / Rachika / Anand | Identified (external). Offer to be rolled out. | - Will proceed with external candidate Debashish Dalui and onboard him by 2/17. - Digital Team's recommended candidate Simon Albett in UK who has helped with Digital Transformation engagements is no longer with Mastek and not an option.
1.1.4 | Technical Lead | 2025-03-02 | 2025-11-02 | Karthik Hari / Rachika / Anand | Identified (external). Final discussion set with Program team post which offer to be rolled out by 2/11 | Have 2 identified candidates - Shine Jose and Reshma Sai. Final level discussion scheduled Friday/Monday and will identify close by 2/11
1.1.5 | DevOps Lead | 2025-03-02 | 2025-11-02 | Karthik Hari / Rachika / Anand | Identified (internal) | Locked in Vishnu who is currently working in Paragon Health Will confirm with Karthik / Rachika and close by 2/10
1.1.6 | Test Process Lead | 2025-03-02 | 2025-11-02 | Chetan / Karthik Hari / Rachika / Anand | Identified (internal) | Internal candidate (Ajit) along with Kartik Ganesan from CEMS PreSales can be positioned for this assessment for 2-4 weeks within the Discovery phase. Will confirm with Chetan/Rachika and close by 2/10
1.2 | Onboard new resources identified for Discovery program (Asset, Logistics, Travel planning, Mandatory Trainings etc) | 2025-07-02 | 02-17-2025 | Anand / Ramesh / Rachika | Yet to start
1.3 | Prepare Questionnaire to understand Recuro's application landscape, scope of applications for modernization, pain areas etc | 2025-07-02 | 02-17-2025 | Ramesh / Anand / new BA | Yet to start
1.4 | Prepare Key Recuro Stakeholder list, Availability, location and logistics etc | 2025-10-02 | 02-17-2025 | Janet | Yet to start
1.5 | Prepare Stakeholder / App-wise questionnaire for assessment of current state | 2025-07-02 | 02-17-2025 | Ramesh / Anand / new BA | Yet to start
1.6 | Introduction of Anand/Ramesh with Recuro CTO/SVP: Ash and ensure alignment on discovery activities/schedule | 02-17-2025 | 02-21-2025 | Vijay Iyer / Janet / Sree | Yet to start
1.7 | Prepare Interview calendar and Schedule of Assessments by application / stakeholder | 02-18-2025 | 02-21-2025 | Ramesh | Yet to start
1.8 | Evaluate tools/accelerators/frameworks like CAST / Jetbrains / Ana.ai for accelerating reverse engineering | 2025-07-02 | 02-21-2025 | Chetan / Kalyan / Ramesh | Yet to start | Recurring discussions set up for week of 2/10 onwards with Digital team (Chetan, Kalyan, Ramesh and Kartik Ganesan)
1.9 | Recuro Discovery / HLS Workshop/Training for identified Mastek Team members for discovery engagement; Expectation setting, Scope, Schedule, Deliverables overview | 02-17-2025 | 02-21-2025 | Sree, Anand, Ramesh | Yet to start
1.10 | Mastek Internal PM operational process training | 02-17-2025 | 02-21-2025 | Rachika, Kevin Lim, Ramesh | Yet to start
1.11 | Finalize Travel plans for Mastek Core Team | 2025-07-02 | 02-19-2025 | Anand / Ramesh | Yet to start
1.12 | Consolidate process assets and templates ahead of Discovery start from prior engagements | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika | Yet to start
1.12.1 | Questionnaires | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.2 | Project Workbook | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.3 | Stakeholder Matrix | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.4 | Key Business KPIs for Virtual Health Platform | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.5 | Key Industry benchmarks related market research content | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.6 | Deliverable Templates: 1. Technology Strategy Document | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.7 | Deliverable Templates: 2. Data & Analytics modernization roadmap | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.8 | Deliverable Templates: 3. Enterprise Architecture Blueprint | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.9 | Deliverable Templates: 4. DevOps Process & Strategy Recommendation | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.10 | Deliverable Templates: 5. Testing Process Strategy Recommendation | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.11 | Deliverable Templates: 6. Tools & Tech Stack recommendation | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.12 | Deliverable Templates: 7. Governance Model | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.13 | Deliverable Templates: 8. Discovery Presentation Deck samples | 2025-07-02 | 02-17-2025 | Ramesh/Chetan/Rachika
1.12.14 | Project Governance Templates: Weekly/QBR deck templates for Recuro and Mastek Executive Leaders briefing | 2025-07-02 | 02-17-2025 | Ramesh/Anand
1.12.15 | Issue/Risk Log template | 2025-07-02 | 02-17-2025 | Ramesh/Anand